## Pre-app
NSIPs and large-scale energy projects progress
Last update 01/08/2023
Project name | Type | Location | BMSDC reference* | Status | Last action | Project website
Bramford to Twinstead | Overhead / underground power lines | Bramford to Twinstead | DC/21/01605 | Submitted / accepted | Application has been accepted for examination. Officers are preparing Local Impact Report. Rule 6 letter / examination timetable expected w/c 7th August. | https://bramford-twinstead.nationalgrid.com/consultation/our-proposals/ and https://infrastructure.planninginspectorate.gov.uk/projects/eastern/bramford-to-twinstead/
Copdock interchange | Highway works | Copdock / Belstead | DC/21/06027 | Pre-app | Options consultation report published 25th March 2022. Awaiting update from DfT and publication of RIS3 (expected 2024) | https://nationalhighways.co.uk/our-work/pipeline-of-possible-future-schemes/a14-junction-55-copdock-interchange/
Norwich to Tilbury (formerly EA Green and ATNC / AENC) | Overhead lines | Norfolk-Suffolk-Essex | DC/21/05611 | Pre-app | Current non-statutory consultation 27th June to 12st August 2023. Officers are preparing a response. Statutory consultation expected Q1 2024. Submission to PINS expected 2024.Ongoing pre-application meetings. Ground investigation works along the route expected August 2023-August 2024 | https://www.nationalgrid.com/electricity-transmission/network-and-infrastructure/infrastructure-projects/norwich-to-tilbury
5 Estuaries | Offshore wind farm | Offshore and Essex (grid connection in the Ardleigh area to be shared with Norwich to Tilbury) | DC/21/05734 | Pre-app | Ongoing pre-app engagement. | https://fiveestuaries.co.uk/
North Falls | Offshore wind farm | Offshore and Essex (grid connection in the Ardleigh area to be shared with Norwich to Tilbury) | DC/21/04710 | Pre-app | Ongoing pre-app engagement. | https://www.northfallsoffshore.com/
Green Switch Capital | Solar farm | Bentley | DC/22/04255 and DC/22/03371 | EIA Screening and pre-app | Screening opinion published Aug 22. Possible application . | https://gscapital.co.uk
WP Grid Services | Grid stability infrastructure | Bramford | DC/21/06759 | EIA Screening | Screening opinion published Dec 2021. Awaiting further contact - possible pre-app / application submission. | https://www.welshpower.com/index.html
Aura Power | Solar farm | Palgrave | DC/22/02592, DC/22/05600 and DC/23/02362 | Pre-app, EIA screening and EIA scoping | Pre-app enquiry completed. EIA screening opinion published. EIA scoping issued. | https://www.aurapower.com/
RNA Energy | Solar farm | Burstall and Hintlesham | DC/22/03498 | Pre-app | Pre-app enquiry completed. Possible application. | https://www.rna-energy.com/
Pegasus group | Solar farm | Boxted | DC/22/04456 and DC/22/06236 | Pre-app and EIA screening | Pre-app enquiry completed. EIA screening published. Scheme design progressing to include BESS. Further pre-app possible. Application expected September / October 2023. | https://www.pegasusgroup.co.uk/
DLP consultants | Solar farm | Earl Stonham | DC/22/05886 and DC/23/01385 | Pre-app and EIA screening | Pre-app enquiry completed. Screening opinion published. Application expected this / next week. | www.dlpconsultants.co.uk
LGT | Solar farm | Brent Eleigh, Lavenham | DC/23/00974 | Pre-app | Pre-app enquiry completed. | https://www.lgtwm.com/uk-en/
The Marquis PH | Solar farm | Layham | DC/23/01435 | Pre-app | Pre-app enquiry completed. | N/A
Clearstone Energy | BESS | Bramford | DC/23/01845 | Pre-app | Pre-app enquiry completed. | https://www.clearstoneenergy.com/
*Pre-app discussions are confidential and the associated references will not show on the public website
KEY | Pre-app / pre-submision stage
Submitted and pending determination
Granted / consented but not yet implemented
Under construction / built and operational
Refused

## Live apps
NSIPs and large-scale energy projects progress
Last update 01/08/2023
Project name | Type | Location | BMSDC reference* | Status | Last action | Project website
Anglian Water strategic pipeline | Water pipeline | Bury St Edmunds to Ipswich to Colchester | DC/22/06352 and DC/22/06309 | Application pending determination | Re-consultation ends this week. Possible further re-consultation. Case officer preparing report. | https://www.anglianwater.co.uk/about-us/our-strategies-and-plans/new-water-pipelines/bury-st-edmunds-to-colchester/
EDF | Solar farm | Bramford | DC/21/04711 | Application pending determination | Officers preparing report for Committee | https://www.edf-re.uk/our-sites/tye-lane
Elgin Energy | Solar farm | Badley | DC/22/01530 | Application pending determination | Officers reviewing application and preparing for presentation to Committee | https://www.elgin-energy.com/
PACE | Solar Farm | Palgrave | DC/22/02667 | Application pending determination | Further information submitted, re-consultation due to start shortly. | http://www.pathfinderce.com/
Statkraft | Solar Farm | Burstall / Flowton / Somersham | DC/22/00683 and DC/22/01243 | Applications pending determination | First consultation closed. Applicant is considering issues raised an intending to submit revised / further information. Re-consultation expected shortly. | https://www.statkraft.co.uk/about-statkraft-uk/where-we-operate/Locations/greybarnsolar/
ENSO | Solar farm | Bramford / Burstall | DC/23/02118 | Application pending determination | This is a resubmission of DC/20/05895. Officers preparing report for Committee | https://ensoenergy.co.uk/enso-projects/bramford/
*Pre-app discussions are confidential and the associated references will not show on the public website
KEY | Pre-app / pre-submision stage
Submitted and pending determination
Granted / consented but not yet implemented
Under construction / built and operational
Refused

## Determined
NSIPs and large-scale energy projects progress
Last update 01/08/2023
Project name | Type | Location | BMSDC reference* | Status | Last action | Project website
Chilton Industrial Estate | Solar array | Sudbury | DC/22/02948 | Granted 24/8/22 | Although this proposal is for a small scale development (<1MW) it is included on the basis of potential cumulative impacts and policy conflict. | https://www.jcshi-torque.co.uk/
EA1 | Sub station for underground cable from offshore wind farm | Bramford | 0116/14 and 2315/11 | Operational. | Completed and operational. Ongoing monitoring and meetings. | https://www.scottishpowerrenewables.com/pages/east_anglia_one.aspx
EA3 | Converter station for underground cables from offshore wind farm | Bramford | 3490/12 | Under construction | Under construction. Ongoing meetings. Further Discharge of Requirement submissions expected shortly. | https://www.scottishpowerrenewables.com/pages/east_anglia_three_background.aspx
Progress Power | Gas-fired power station | Eye | DC/21/03894 | Under construction. Ongoing community liaison meetings. | Ongoing discharge of requirements and discussion about minor amendments. Engagement with developer and community. | https://www.drax.com/about-us/our-projects/progress-power/
RNA Energy | Solar farm | Rickinghall | DC/21/06825 | Application determined | Refused at Committee 3rd August 2022. Appeal submitted and started. Officers preparing Statement of Case. Decision expected August / September | https://www.rna-energy.com/
ENSO | Solar farm | Burstall / Flowton / Somersham | DC/20/05895 and DC/21/00060 | Applications determined | Babergh Granted, Mid Suffolk Refused - appeal in progress. Inquiry starts 15th August. Decision expected September. | https://ensoenergy.co.uk/enso-projects/bramford/
Conrad Energy | Grid stability infrastructure | Yaxley | DC/22/04021 | Application determined | Granted | https://conradenergy.co.uk/
Conrad Energy | Synchronous condenser | Yaxley | DC/23/01494 | Application determined | Granted | https://conradenergy.co.uk/
*Pre-app discussions are confidential and the associated references will not show on the public website
KEY | Pre-app / pre-submision stage
Submitted and pending determination
Granted / consented but not yet implemented
Under construction / built and operational
Refused